## Sheet1
Unique ID | User Story | Stroy Points | Assignee | Reviewer 1 | Reviewer 2 | Depends On | Name: | Points: | Reviews
1 | As an unregistered user / registered user I should be able to view the Electronic Journals of approved companies | 5 | Yousef Diaa | Zeyad Khattab | Omar Samy |  | Abdulrahman Muhammad | 11 | 4
[7 empty] | Ahmad Yousef | 5 | 4
2 | As a reviewer i should be able to assign myself a case | 2 | Ahmed Shams | Mohamad Mantawy | Mohamed Adel |  | Abdelrahman Ouda | 2 | 4
3 | As a lawyer i should be able to assign myself a case | 2 | Ahmed Shams | Mohamad Mantawy | Mohamed Adel |  | Yousef Diaa | 8 | 3
[7 empty] | Fadi Essam | 3 | 4
4 | As an investor i should be able to ask a lawyer to start working on my case | 1 | Mohamad Mantawy | Ahmed Shams | Mohamed Adel |  | Mohamed Adel | 10 | 3
[7 empty] | Zeyad Khattab | 7 | 3
5 | As an investor I should be able to log in to the external portal | 2 | Mohamed Adel | Ahmed Shams | Mohamad Mantawy |  | Ahmed Shams | 6 | 3
[7 empty] | Mohamad Mantawy | 4 | 3
| As an investor i should be able to reset my password in case i lose it. | 5 | Mohamed Adel | Ahmed Shams | Yahia Badr |  | Yahia Badr | 7 | 4
| As an admin i should be able to reset my password in case i lose it. | 1 | Mohamed Adel | Ahmed Shams | Yahia Badr |  | Omar Samy | 9 | 4
| As a reviewer i should be able to reset my password in case i lose it. | 1 | Mohamed Adel | Ahmed Shams | Yahia Badr |  | Average: | 6.5455 | 3.5455
| As a lawyer i should be able to reset my password in case i lose it. | 1 | Mohamed Adel | Ahmed Shams | Yahia Badr |  | Total: | 72 | 39
6 | As an admin I should be able to view the name of the last lawyer who worked on a specific case from the cases page | 1 | Yousef Diaa | Zeyad Khattab | Omar Samy
7 | As a reviewer I should be able to view the name of the last lawyer who worked on a specific case from the cases page | 1 | Yousef Diaa | Zeyad Khattab | Omar Samy
8 | As a lawyer I should be able to view the name of the last lawyer who worked on a specific case from the cases page | 1 | Yousef Diaa | Zeyad Khattab | Omar Samy
9 | As an admin I should be able to open and view the details of all the cases in the system in the cases page | 2 | Yahia Badr | Fadi Essam | Abdulrahman Muhammad
10 | As a reviewer I should be able to open and view the details of all the cases in the system in the cases page | 1 | Yahia Badr | Fadi Essam | Abdulrahman Muhammad
11 | As a lawyer I should be able to open and view the details of all the cases in the system in the cases page | 1 | Yahia Badr | Fadi Essam | Abdulrahman Muhammad
12 | As a lawyer I should be able to sort my tasks by "Case ID" or "Case Creation Date" | 2 | Fadi Essam | Omar Samy | Yousef Diaa
13 | As a reviewer I should be able to sort my tasks by "Case ID" or "Case Creation Date" | 1 | Fadi Essam | Omar Samy | Yousef Diaa
14 | As a lawyer I should be able to view all my due tasks in my work page | 2 | Mohamad Mantawy | Yahia Badr | Fadi Essam
15 | As a reviewer I should be able to view all my due tasks in my work page | 1 | Mohamad Mantawy | Yahia Badr | Fadi Essam
16 | As a lawyer I should be able to add a comment on a rejected company establishment form made by an investor | 3 | Omar Samy | Zeyad Khattab | Yousef Diaa
17 | As a reviewer I should be able to add a comment on a rejected company establishment form | 1 | Omar Samy | Zeyad Khattab | Yousef Diaa
18 | As a lawyer I should be able to accept or reject a company establishment form made by an investor | 1 | Ahmed Shams | Yahia Badr | Fadi Essam
19 | As a reviewer I should be able to accept or reject a company establishment form | 1 | Ahmed Shams | Yahia Badr | Fadi Essam
20 | As an investor I should be able to edit my profile | 3 | Abdulrahman Muhammad | Abdelrahman Ouda | Ahmad Yousef
21 | As an investor I should be able to get notified when I am required to pay the fees after the approval of my company request | 1 | Zeyad Khattab | Omar Samy | Yahia Badr
22 | As an investor I should be able to update my company establishment form | 2 | Abdelrahman Ouda | Abdulrahman Muhammad | Ahmad Yousef
23 | As a lawyer I should be able to view a company establishment form made by an investor | 2 | Yahia Badr | Mohamed Adel | Mohamad Mantawy
24 | As a reviewer I should be able to view a company establishment form that is reviewed or made by a lawyer | 1 | Yahia Badr | Mohamed Adel | Mohamad Mantawy
25 | As a lawyer I should be able to regenerate documents that were generated from a company establishment form after editing anything in that form | 5 | Omar Samy | Ahmad Yousef | Fadi Essam
26 | As an external entities I should be able to receive a generated contract in “PDF” format or SSC companies after a lawyer has filled a company establishment form | 5 | Ahmad Yousef | Abdelrahman Ouda | Abdulrahman Muhammad
27 | As an external entities I should be able to receive a generated decision in “PDF” format or SPC companies after a lawyer has filled a company establishment form | 5 | Zeyad Khattab | Abdelrahman Ouda | Abdulrahman Muhammad
28 | As an external entities I should be able to receive an update if a new company has been established | 1 | Zeyad Khattab | Abdelrahman Ouda | Abdulrahman Muhammad
29 | As an admin i should be able to upload a json file to add a new company type in the cases | 8 | Abdulrahman Muhammad | Yousef Diaa | Ahmad Yousef
72