## Sheet1
Unique ID | User Story | Stroy Points | Assignee | Reviewer 1 | Reviewer 2 | Depends On | Needs Testing | Name: | Points: | Reviews
1 | Create Investor (Mongo) | 2 | Abdulrahman Muhammad | Omar Samy | Fadi Essam |  |  | Abdulrahman Muhammad | 10 | 3
2 | Read Investor (Mongo) | 1 | Abdulrahman Muhammad | Omar Samy | Fadi Essam |  |  | Ahmad Yousef | 14 | 3
3 | Update Investor (Mongo) | 1 | Abdulrahman Muhammad | Omar Samy | Fadi Essam |  |  | Abdelrahman Ouda | 13 | 3
4 | Delete Investor (Mongo) | 1 | Abdulrahman Muhammad | Omar Samy | Fadi Essam |  |  | Yousef Diaa | 10 | 3
[8 empty] | Fadi Essam | 13 | 3
5 | Create Lawyer (Mongo) | 2 | Ahmad Yousef | Ahmed Shams | Mohamad Mantawy |  |  | Mohamed Adel | 10 | 4
6 | Read Lawyer (Mongo) | 1 | Ahmad Yousef | Ahmed Shams | Mohamad Mantawy |  |  | Omar Samy | 13 | 3
7 | Update Lawyer (Mongo) | 1 | Ahmad Yousef | Ahmed Shams | Mohamad Mantawy |  |  | Zeyad Khattab | 10 | 4
8 | Delete Lawyer (Mongo) | 1 | Ahmad Yousef | Ahmed Shams | Mohamad Mantawy |  |  | Ahmed Shams | 10 | 3
[8 empty] | Mohamad Mantawy | 10 | 4
9 | Create Reviewer (Mongo) | 2 | Abdelrahman Ouda | Yahia Badr | Mohamad Mantawy |  |  | Yahia Badr | 10 | 3
10 | Read Reviewer (Mongo) | 1 | Abdelrahman Ouda | Yahia Badr | Mohamad Mantawy |  |  |  | Total: 123 | Total: 36
11 | Update Case (Mongo) | 1 | Abdelrahman Ouda | Yahia Badr | Mohamad Mantawy |  |  |  | Avg: 11.2 | Avg: 3.4
12 | Delete Reviewer (Mongo) | 1 | Abdelrahman Ouda | Yahia Badr | Mohamad Mantawy
13 | Create Admin (Mongo) | 2 | Yousef Diaa | Mohamed Adel | Ahmad Yousef
14 | Read Admin (Mongo) | 1 | Yousef Diaa | Mohamed Adel | Ahmad Yousef
15 | Update Admin (Mongo) | 1 | Yousef Diaa | Mohamed Adel | Ahmad Yousef
16 | Delete Admin (Mongo) | 1 | Yousef Diaa | Mohamed Adel | Ahmad Yousef
17 | Create Case (Mongo) | 2 | Fadi Essam | Zeyad Khattab | Yousef Diaa
18 | Read Case (Mongo) | 1 | Fadi Essam | Zeyad Khattab | Yousef Diaa
19 |  | 1 | Fadi Essam | Zeyad Khattab | Yousef Diaa
20 | Delete Case (Mongo) | 1 | Fadi Essam | Zeyad Khattab | Yousef Diaa
21 | Create Company (Mongo) | 2 | Mohamed Adel | Abdulrahman Muhammad | Yousef Diaa
22 | Read Company (Mongo) | 1 | Mohamed Adel | Abdulrahman Muhammad | Yousef Diaa
23 | Update Company (Mongo) | 1 | Mohamed Adel | Abdulrahman Muhammad | Yousef Diaa
24 | Delete Company (Mongo) | 1 | Mohamed Adel | Abdulrahman Muhammad | Yousef Diaa
25 | Create External Entity (Mongo) | 2 | Omar Samy | Mohamed Adel | Yahia Badr
26 | Read External Entity (Mongo) | 1 | Omar Samy | Mohamed Adel | Yahia Badr
27 | Update External Entity (Mongo) | 1 | Omar Samy | Mohamed Adel | Yahia Badr
28 | Delete External Entity (Mongo) | 1 | Omar Samy | Mohamed Adel | Yahia Badr
29 | Create Notification (Mongo) | 2 | Zeyad Khattab | Fadi Essam | Abdelrahman Ouda
30 | Read Notification (Mongo) | 1 | Zeyad Khattab | Fadi Essam | Abdelrahman Ouda
31 | Update Notification (Mongo) | 1 | Zeyad Khattab | Fadi Essam | Abdelrahman Ouda
32 | Delete Notification (Mongo) | 1 | Zeyad Khattab | Fadi Essam | Abdelrahman Ouda
From the Backlog
(2.4) 33 | As an investor I should be able to fill a company establishment form, so that I establish a new company. | 8 | Abdelrahman Ouda | Omar Samy | Mohamad Mantawy
(5.1) 34 | As a lawyer I should be able to fill a company establishment form, so that I establish a new company. | 8 | Fadi Essam | Omar Samy | Mohamad Mantawy
(2.5) 35 | As an investor I should be able to keep track of my company establishment request, so that I am aware of its current status. | 5 | Yousef Diaa | Zeyad Khattab | Ahmad Yousef
(2.8) 36 | As an investor I should be able to view the fees of my approved company establishment request, so that I am aware of the amount of money needed. | 5 | Zeyad Khattab | Ahmed Shams | Abdulrahman Muhammad
(4.1) 37 | As a lawyer I should be able to view all my due tasks in my work page, so that I am aware of the tasks I am required to fulfill. | 5 | Mohamad Mantawy | Yousef Diaa | Mohamed Adel
(4.1) 38 | As a reviewer I should be able to view all my due tasks in my work page, so that I am aware of the tasks I am required to fulfill. | 5 | Mohamad Mantawy | Yousef Diaa | Mohamed Adel
(5.2) 39 | As a lawyer I should be able to view a company establishment form made by an investor, so that I can review it. | 5 | Yahia Badr | Abdelrahman Ouda | Abdulrahman Muhammad
(6.1) 40 | As a reviewer I should be able to view a company establishment form that is reviewed or made by a lawyer, so that I can review it. | 5 | Yahia Badr | Abdelrahman Ouda | Abdulrahman Muhammad
(5.3) 41 | As a lawyer I should be able to accept or reject a company establishment form made by an investor, so that it can be further reviewed by a reviewer or be updated by the investor. | 5 | Ahmed Shams | Omar Samy | Ahmad Yousef
(6.2) 42 | As a reviewer I should be able to accept or reject a company establishment form, so that it can be accepted or be updated by the lawyer. | 5 | Ahmed Shams | Omar Samy | Ahmad Yousef
(2.7) 43 | As an investor I should be able to update my company establishment form, so that I can change or correct its content. | 5 | Abdulrahman Muhammad | Mohamad Mantawy | Yahia Badr
(2.10) 45 | As an investor I should be able to view the lawyer’s comments on my company establishment form, so that I know what should be changed or updated in my form. | 5 | Mohamed Adel | Fadi Essam | Ahmed Shams
(2.11) 46 | As an investor I should be able to view all my companies, so that I have a history of my created / pending companies. | 8 | Omar Samy | Zeyad Khattab | Abdelrahman Ouda
(3.2) 47 | As a lawyer I should be able to view all the cases in the system in the cases page, so that I am able to know the all the cases in the system. | 3 | Ahmad Yousef | Zeyad Khattab | Mohamed Adel
(3.2) 48 | As a reviewer I should be able to view all the cases in the system in the cases page, so that I am able to know the all the cases in the system. | 3 | Ahmad Yousef | Zeyad Khattab | Mohamed Adel
(3.2) 49 | As a admin I should be able to view all the cases in the system in the cases page, so that I am able to know the all the cases in the system. | 3 | Ahmad Yousef | Zeyad Khattab | Mohamed Adel