## Sheet1
Unique ID | User Story | Stroy Points | Assignee | Reviewer 1 | Reviewer 2 | Depends On | Name: | Points: | Reviews
1 | Create Investor (Jest) | 1 | Abdulrahman Muhammad | Abdelrahman Ouda | Ahmad Yousef |  | Abdulrahman Muhammad | 19 | 5
2 | Read Investor (Jest) | 1 | Abdulrahman Muhammad | Abdelrahman Ouda | Ahmad Yousef |  | Ahmad Yousef | 10 | 6
3 | Update Investor (Jest) | 1 | Abdulrahman Muhammad | Abdelrahman Ouda | Ahmad Yousef |  | Abdelrahman Ouda | 10 | 6
4 | Delete Investor (Jest) | 1 | Abdulrahman Muhammad | Abdelrahman Ouda | Ahmad Yousef |  | Yousef Diaa | 12 | 6
[7 empty] | Fadi Essam | 12 | 6
5 | Create Lawyer (Jest) | 1 | Ahmad Yousef | Yahia Badr | Mohamad Mantawy |  | Mohamed Adel | 14 | 5
6 | Read Lawyer (Jest) | 1 | Ahmad Yousef | Yahia Badr | Mohamad Mantawy |  | Omar Samy | 14 | 5
7 | Update Lawyer (Jest) | 1 | Ahmad Yousef | Yahia Badr | Mohamad Mantawy |  | Zeyad Khattab | 14 | 5
8 | Delete Lawyer (Jest) | 1 | Ahmad Yousef | Yahia Badr | Mohamad Mantawy |  | Ahmed Shams | 12 | 5
[7 empty] | Mohamad Mantawy | 12 | 6
9 | Create Reviewer (Jest) | 1 | Abdelrahman Ouda | Zeyad Khattab | Mohamed Adel |  | Yahia Badr | 12 | 5
10 | Read Reviewer (Jest) | 1 | Abdelrahman Ouda | Zeyad Khattab | Mohamed Adel |  | Average: | 12.8182 | 5.4545
11 | Update Reviewer (Jest) | 1 | Abdelrahman Ouda | Zeyad Khattab | Mohamed Adel |  | Total: | 141 | 60
12 | Delete Reviewer (Jest) | 1 | Abdelrahman Ouda | Zeyad Khattab | Mohamed Adel
13 | Create Admin (Jest) | 1 | Yousef Diaa | Ahmed Shams | Abdulrahman Muhammad
14 | Read Admin (Jest) | 1 | Yousef Diaa | Ahmed Shams | Abdulrahman Muhammad
15 | Update Admin (Jest) | 1 | Yousef Diaa | Ahmed Shams | Abdulrahman Muhammad
16 | Delete Admin (Jest) | 1 | Yousef Diaa | Ahmed Shams | Abdulrahman Muhammad
17 | Create Case (Jest) | 2 | Fadi Essam | Yousef Diaa | Omar Samy
18 | Read Case (Jest) | 1 | Fadi Essam | Yousef Diaa | Omar Samy
19 | Update Case (Jest) | 2 | Fadi Essam | Yousef Diaa | Omar Samy
20 | Delete Case (Jest) | 1 | Fadi Essam | Yousef Diaa | Omar Samy
21 | Create Company (Jest) | 1 | Mohamed Adel | Fadi Essam | Yousef Diaa
22 | Read Company (Jest) | 1 | Mohamed Adel | Fadi Essam | Yousef Diaa
23 | Update Company (Jest) | 1 | Mohamed Adel | Fadi Essam | Yousef Diaa
24 | Delete Company (Jest) | 1 | Mohamed Adel | Fadi Essam | Yousef Diaa
25 | Create External Entity (Jest) | 1 | Omar Samy | Yahia Badr | Fadi Essam
26 | Read External Entity (Jest) | 1 | Omar Samy | Yahia Badr | Fadi Essam
27 | Update External Entity (Jest) | 1 | Omar Samy | Yahia Badr | Fadi Essam
28 | Delete External Entity (Jest) | 1 | Omar Samy | Yahia Badr | Fadi Essam
29 | Create Notification (Jest) | 1 | Zeyad Khattab | Omar Samy | Abdelrahman Ouda
30 | Read Notification (Jest) | 1 | Zeyad Khattab | Omar Samy | Abdelrahman Ouda
31 | Update Notification (Jest) | 1 | Zeyad Khattab | Omar Samy | Abdelrahman Ouda
32 | Delete Notification (Jest) | 1 | Zeyad Khattab | Omar Samy | Abdelrahman Ouda
Jest of previous User Stories
(2.4) 33 | As an investor I should be able to fill a company establishment form, so that I establish a new company.(Jest) | 2 | Abdelrahman Ouda | Zeyad Khattab | Ahmed Shams
(5.1) 34 | As a lawyer I should be able to fill a company establishment form, so that I establish a new company.(Jest) | 2 | Fadi Essam | Zeyad Khattab | Ahmed Shams
(2.5) 35 | As an investor I should be able to keep track of my company establishment request, so that I am aware of its current status.(Jest) | 2 | Yousef Diaa | Abdulrahman Muhammad | Mohamad Mantawy
(2.8) 36 | As an investor I should be able to view the fees of my approved company establishment request, so that I am aware of the amount of money needed.(Jest) | 2 | Zeyad Khattab | Mohamed Adel | Ahmad Yousef
(4.1) 37 | As a lawyer I should be able to view all my due tasks in my work page, so that I am aware of the tasks I am required to fulfill.(Jest) | 2 | Mohamad Mantawy | Mohamed Adel | Yahia Badr
(4.1) 38 | As a reviewer I should be able to view all my due tasks in my work page, so that I am aware of the tasks I am required to fulfill.(Jest) | 2 | Mohamad Mantawy | Mohamed Adel | Yahia Badr
(5.2) 39 | As a lawyer I should be able to view a company establishment form made by an investor, so that I can review it.(Jest) | 2 | Yahia Badr | Mohamad Mantawy | Ahmed Shams
(6.1) 40 | As a reviewer I should be able to view a company establishment form that is reviewed or made by a lawyer, so that I can review it.(Jest) | 2 | Yahia Badr | Mohamad Mantawy | Ahmed Shams
(5.3) 41 | As a lawyer I should be able to accept or reject a company establishment form made by an investor, so that it can be further reviewed by a reviewer or be updated by the investor.(Jest) | 2 | Ahmed Shams | Yousef Diaa | Zeyad Khattab
(6.2) 42 | As a reviewer I should be able to accept or reject a company establishment form, so that it can be accepted or be updated by the lawyer.(Jest) | 2 | Ahmed Shams | Yousef Diaa | Zeyad Khattab
(2.7) 43 | As an investor I should be able to update my company establishment form, so that I can change or correct its content.(Jest) | 2 | Abdulrahman Muhammad | Abdelrahman Ouda | Ahmad Yousef
(2.10) 45 | As an investor I should be able to view the lawyer’s comments on my company establishment form, so that I know what should be changed or updated in my form.(Jest) | 2 | Mohamed Adel | Abdulrahman Muhammad | Omar Samy
(2.11) 46 | As an investor I should be able to view all my companies, so that I have a history of my created / pending companies.(Jest) | 2 | Omar Samy | Fadi Essam | Yousef Diaa
(3.2) 47 | As a lawyer I should be able to view all the cases in the system in the cases page, so that I am able to know the all the cases in the system.(Jest) | 2 | Ahmad Yousef | Abdulrahman Muhammad | Yahia Badr
(3.2) 48 | As a reviewer I should be able to view all the cases in the system in the cases page, so that I am able to know the all the cases in the system.(Jest) | 2 | Ahmad Yousef | Abdulrahman Muhammad | Yahia Badr
(3.2) 49 | As a admin I should be able to view all the cases in the system in the cases page, so that I am able to know the all the cases in the system.(Jest) | 2 | Ahmad Yousef | Abdulrahman Muhammad | Yahia Badr
New User Stories With Jest
50(2.1) | As an investor I should be able to register on the external portal, so that I can have an account on the portal. | 5 | Ahmed Shams | Abdelrahman Ouda | Fadi Essam
| As an investor I should be able to register on the external portal, so that I can have an account on the portal.(Jest) | 3 | Ahmed Shams | Abdelrahman Ouda | Fadi Essam
51(7.1) | As an admin I should be able to register entity employees, so that they can log in and use the internal portal. | 5 | Mohamad Mantawy | Ahmed Shams | Ahmad Yousef
| As an admin I should be able to register entity employees, so that they can log in and use the internal portal.(Jest) | 3 | Mohamad Mantawy | Ahmed Shams | Ahmad Yousef
52(2.2) | As an investor I should be able to log in to the external portal, so that I can use the system’s facilities. | 5 | Mohamed Adel | Mohamad Mantawy | Omar Samy
| As an investor I should be able to log in to the external portal, so that I can use the system’s facilities.(Jest) | 3 | Mohamed Adel | Mohamad Mantawy | Omar Samy
53(3.1) | As a lawyer / reviewer / admin I should be able to log in to the internal portal, so that I can use the system’s facilities. | 5 | Yahia Badr | Mohamed Adel | Zeyad Khattab
| As a lawyer / reviewer / admin I should be able to log in to the internal portal, so that I can use the system’s facilities.(Jest) | 3 | Yahia Badr | Mohamed Adel | Zeyad Khattab
54(2.9) | As an investor I should be able to pay the fees of my approved company establishment request, so that I do not need to pay the fees in person. | 8 | Abdulrahman Muhammad | Ahmad Yousef | Mohamad Mantawy
| As an investor I should be able to pay the fees of my approved company establishment request, so that I do not need to pay the fees in person.(Jest) | 5 | Abdulrahman Muhammad | Ahmad Yousef | Mohamad Mantawy
55(2.3) | edit my profile, so that I can update my information. | (Done)
| edit my profile, so that I can update my information.(Jest) | (Done)
56(2.6) | As an investor I should be able to get notified when I am required to pay the fees after the approval of my company request, so that I do not need to always check my request’s status. | 5 | Zeyad Khattab | Abdelrahman Ouda | Mohamed Adel
| As an investor I should be able to get notified when I am required to pay the fees after the approval of my company request, so that I do not need to always check my request’s status.(Jest) | 3 | Zeyad Khattab | Abdelrahman Ouda | Mohamed Adel
57(3.3) | As a lawyer / reviewer / admin I should be able to open and view the details of all the cases in the system in the cases page, so that I am able to know the details of each case in the system. | (Done)
| As a lawyer / reviewer / admin I should be able to open and view the details of all the cases in the system in the cases page, so that I am able to know the details of each case in the system.(Jest) | (Done)
58(3.4) | As a Entity Employee (Lawyer / Reviewer) / Admin i should be able to view the name of the last lawyer who worked on a specific case from the cases page. | 1 | Yousef Diaa | Zeyad Khattab | Abdulrahman Muhammad
| As a Entity Employee (Lawyer / Reviewer) / Admin i should be able to view the name of the last lawyer who worked on a specific case from the cases page.(Jest) | 2 | Yousef Diaa | Zeyad Khattab | Abdulrahman Muhammad
59(4.2) | As a Lawyer / Reviewer i should be able to sort my tasks by "Case ID" or "Case Creation Date", so that I can have a better overview of my assigned tasks. | 2 | Fadi Essam | Omar Samy | Ahmed Shams
| As a Lawyer / Reviewer i should be able to sort my tasks by "Case ID" or "Case Creation Date", so that I can have a better overview of my assigned tasks.(Jest) | 2 | Fadi Essam | Omar Samy | Ahmed Shams
60(5.4) | As a Lawyer i should be able to add a comment on a rejected company establishment form made by an investor, so that the investor is aware of the required changes in the form. | 2 | Omar Samy | Fadi Essam | Yousef Diaa
| As a Lawyer i should be able to add a comment on a rejected company establishment form made by an investor, so that the investor is aware of the required changes in the form.(Jest) | 2 | Omar Samy | Fadi Essam | Yousef Diaa
61(5.5) | As a Lawyer i should be able to update a company establishment form made by myself, so that I can change or correct its content. | 2 | Abdelrahman Ouda | Yahia Badr | Mohamad Mantawy
| As a Lawyer i should be able to update a company establishment form made by myself, so that I can change or correct its content.(Jest) | 2 | Abdelrahman Ouda | Yahia Badr | Mohamad Mantawy
62(5.7) | As a Lawyer i should be able to recalculate the fees of a company establishment form after editing anything in that form, so that I am able to update the fees. | Removed from Backlog
| As a Lawyer i should be able to recalculate the fees of a company establishment form after editing anything in that form, so that I am able to update the fees.(Jest) | Removed from Backlog
63(6.3) | As a Reviewer i should be able to add a comment on a rejected company establishment form, so that the lawyer is aware of the required changes in the form. | 2 | Omar Samy | Fadi Essam | Yousef Diaa
| As a Reviewer i should be able to add a comment on a rejected company establishment form, so that the lawyer is aware of the required changes in the form.(Jest) | 2 | Omar Samy | Fadi Essam | Yousef Diaa