## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Create Investor | 3 | Abdulrahman Muhammad |  |  | Ronic | 7
2 | Read Investor | 1 | Abdulrahman Muhammad |  |  | Fadi | 7
3 | Update Investor | 3 | Abdulrahman Muhammad |  |  | Yahia | 8
4 | Delete Investor | 2 | Mohamad Mantawy | 1 - Create Investor | YES | Moe | 8
5 | Create Lawyer | 3 | Ahmad Yousef |  |  | Joe | 7
6 | Read Lawyer | 1 | Ahmad Yousef |  |  | Dondo | 9
7 | Update Lawyer | 3 | Ahmad Yousef |  |  | Manta | 5
8 | Delete Lawyer | 2 | Ahmad Yousef |  |  | Shams | 6
9 | Create Reviewer | 3 | Abdelrahman Ouda |  |  | Samy | 7
10 | Read Reviewer | 1 | Abdelrahman Ouda |  |  | Zizo | 6
11 | Update Reviewer | 3 | Abdelrahman Ouda |  |  | Ouda | 7
12 | Delete Reviewer | 2 | Ahmed Shams | 9 - Create Reviewer | YES
13 | Create Admin | 3 | Yousef Diaa
14 | Read Admin | 1 | Yousef Diaa
15 | Update Admin | 3 | Yousef Diaa
16 | Delete Admin | 2 | Ahmed Shams | 13 - Create Admin | YES
17 | Create Case | 5 | Fadi Essam | Stories : [1, 5, 9] | YES
18 | Read Case | 2 | Ahmed Shams | 17 - Create Case | YES
19 | Update Case | 5 | Yahia Badr | 17 - Create Case | YES
20 | Delete Case | 2 | Fadi Essam
21 | Create Company | 3 | Mohamed Adel | Stories: [1, 17] | YES
22 | Read Company | 1 | Mohamad Mantawy | 21 - Create Company | YES
23 | Update Company | 3 | Mohamed Adel
24 | Delete Company | 2 | Mohamed Adel
25 | Create External Entity | 3 | Omar Samy | 17 - Create Case | YES
26 | Read External Entity | 1 | Omar Samy
27 | Update External Entity | 3 | Omar Samy
28 | Delete External Entity | 2 | Mohamad Mantawy | 25 - Create Ext. Entity | YES
29 | Create Notification | 3 | Yahia Badr | Stories: [1, 17] | YES
30 | Read Notification | 1 | Zeyad Khattab | 29 - Create Notification | YES
31 | Update Notification | 3 | Zeyad Khattab | 29 - Create Notification | YES
32 | Delete Notification | 2 | Zeyad Khattab | 29 - Create Notification | YES